SDLC & DEVOPS FUNDAMENTALS

Smart-Attend

Mobile App — Release Manager Assignment

Waterfall Failure Analysis  |  Agile/Scrum Pivot  |  Sprint Backlog

| Role Junior Project Manager | Course SDLC & DevOps Fundamentals | Deadline 14 March 2026 |
| --- | --- | --- |

# Project Scenario

You are the Junior Project Manager for a university startup building the Smart-Attend Student Attendance App. The app leverages GPS Geo-fencing technology to mark student attendance automatically the moment a student physically enters the designated classroom boundary.

⚠️ The Pivot — Mid-Project Requirement Change Halfway through development, the Dean introduces a critical new requirement: Biometric (Face ID) Verification must be integrated to prevent 'proxy' attendance fraud. This pivot forces the team to re-evaluate the chosen Software Development Life Cycle (SDLC) model and pivot strategy.

# Task 1: The 'Waterfall' Failure Analysis

The Waterfall Model is a traditional, sequential SDLC approach in which each phase—Requirements, Design, Development, Testing, and Deployment—must be completed and signed off before the next begins. When the Dean's biometric requirement is introduced mid-development, this rigid structure becomes catastrophically unsuitable. The following three reasons explain why Waterfall would cause a project crisis.

## Failure Reason 1: Structural Rigidity

| RIGID | The Waterfall model assumes that all requirements are known, agreed upon, and frozen before a single line of code is written. The 'Requirements Phase' gate is closed permanently once the project proceeds to Design. Impact on Smart-Attend: By the time the Dean adds the Face ID requirement, the team is already in the Development phase. In Waterfall, there is no formal mechanism to re-enter the Requirements phase. Adding Biometric logic would require: |
| --- | --- |

- Halting active development — disrupting all ongoing coding tasks for geo-fencing.

- Rewriting the Requirements Specification Document (SRS) — a formally approved document.

- Revising the System Architecture and Design blueprints to include camera hardware, biometric APIs (e.g., Apple Face ID SDK), and new data storage for biometric templates.

- Re-obtaining formal sign-off from all stakeholders before proceeding — weeks of delay.

In short: the model's greatest 'strength' (strict phase gates) becomes its greatest weakness when change arrives.

## Failure Reason 2: Prohibitive Cost of Change

| COSTLY | In software engineering, the 'Cost of Change Curve' is a well-established principle: the later a change is introduced in the SDLC, the exponentially higher the cost to implement it. Waterfall projects operate on a fixed 'blueprint' contract; any deviation is treated as a formal Change Request. Impact on Smart-Attend: Adding Biometric verification mid-development would incur massive additional costs: |
| --- | --- |

- Budget Overrun: The project budget was scoped for a geo-fencing app only. Face ID integration requires new licenses (e.g., biometric SDK licensing fees), potentially new hardware, and additional developer hours that were never estimated.

- Schedule Slippage: The 6-month project timeline would need to be extended by potentially 2–3 months, risking the academic year deadline.

- Rework Cost: Code already written for user authentication would likely need to be refactored or completely rebuilt to accommodate biometric verification as a primary or secondary authentication factor.

- Documentation Rework: Every phase document (SRS, Design Doc, Test Plans) must be updated, reviewed, and re-approved — consuming significant PM and stakeholder time.

## Failure Reason 3: Delayed Integration Testing

| LATE | In a 6-month Waterfall cycle, the Testing phase only begins after all development is complete — typically in month 5 or 6. Critical integration bugs, system incompatibilities, and performance issues are discovered only at the very end, leaving no time for meaningful remediation. Impact on Smart-Attend: The Biometric module introduces high-risk integration points that will only be discovered in the final weeks: |
| --- | --- |

- Face ID + Geo-fence Conflict: The biometric verification flow and geo-fence trigger might conflict in timing — e.g., the geo-fence fires before Face ID completes. This would only be caught in end-to-end testing.

- Device Compatibility: Face ID is unavailable on non-Apple devices (Android uses different biometric APIs). Testing this across a diverse student device pool at month 6 leaves zero time to build a cross-platform fallback.

- Privacy & Compliance Failures: Biometric data processing may violate university data privacy policies or regional regulations (e.g., PDPA in India). A Waterfall project would only uncover this in the final review — after architecture is locked.

- No Feedback Loop: Students and faculty have no opportunity to test and provide feedback until the very end. Usability issues discovered post-launch require a completely new project cycle to fix.

# Task 2: The Agile Pivot — Scrum Framework

Switching to the Scrum Framework allows the team to absorb the Dean's new biometric requirement gracefully. Scrum's iterative, time-boxed sprint structure means the project is never 'locked in' — the Product Backlog can be re-prioritized at any Sprint Planning meeting.

## Why Scrum Solves Waterfall's Failures

| Waterfall Failure | Scrum Solution | Smart-Attend Benefit |
| --- | --- | --- |
| Structural Rigidity | Backlog can be updated at any Sprint boundary | Face ID story added to Sprint 2 without stopping Sprint 1 |
| Cost of Change | Small, incremental changes cost far less than late-stage rework | Biometric module built in isolation, reducing refactoring cost |
| Delayed Testing | Testing occurs within every 2-week Sprint | Integration issues caught in Sprint 2 with 2 weeks to fix |

## Sprint 1 (Weeks 1–2): Minimum Viable Product (MVP)

Goal: Ship a working MVP that stakeholders can test immediately. Focus Areas: Basic UI Wireframes, University ID Login, Core Geo-fence Engine

- Build the student-facing mobile UI (login screen, attendance status screen, notification panel).

- Implement University ID / Password authentication using the existing student database API.

- Develop the core Geo-fence engine: detect student GPS coordinates against a 10-meter classroom perimeter using the Google Maps Geofencing API or native iOS/Android region monitoring.

- Trigger automatic attendance marking when a student enters the geo-fence boundary.

- Send push notification to the student confirming attendance has been marked.

- Build the Teacher Dashboard: real-time list of students marked 'Present' for each class.

- Sprint Review: Demo to Dean and Faculty. Collect feedback before Sprint 2.

## Sprint 2 (Weeks 3–4): Biometric Integration & Dashboard Refinement

Goal: Layer Face ID verification on top of the MVP; refine reporting based on Sprint 1 feedback. Focus Areas: Biometric Module, Admin Controls, Reporting Dashboard

- Integrate Apple Face ID (iOS) and Android BiometricPrompt API as a secondary verification step after geo-fence triggers.

- Build the anti-proxy logic: attendance is only confirmed when BOTH geo-fence AND Face ID verification succeed.

- Add manual attendance override for Admin: handle cases of technical failure (Face ID not working, poor GPS signal).

- Refine the Reporting Dashboard based on teacher feedback from Sprint 1: add export to CSV, attendance percentage charts, and date filtering.

- Implement privacy safeguards: biometric data is processed on-device only (no raw biometric data stored on the server, only verification tokens).

- Final UAT (User Acceptance Testing) with a pilot batch of 30 students.

- Sprint Review & Retrospective: Present complete system to the Dean for final approval.

# Task 3: Sprint Backlog — Sprint 1 (MVP)

The Sprint Backlog is a refined subset of the Product Backlog that the development team commits to completing within Sprint 1 (2 weeks / 10 working days). All User Stories follow the standard format: As a [role], I want [feature] so that [benefit].

## Sprint 1 Backlog — Core MVP Stories

| Story ID | User Story | Priority | Est. Hours | Status |
| --- | --- | --- | --- | --- |
| US01 | As a student, I want to log in via my university ID and password so that I can securely access my attendance profile. | High | 4 hrs | ✅ Done |
| US02 | As a teacher, I want to view a real-time list of present students during class so that I can monitor attendance without manual registers. | High | 6 hrs | ✅ Done |
| US03 | As the system, I want to detect if a student's device is within 10 metres of the classroom GPS coordinates so that attendance can be triggered automatically. | High | 8 hrs | ✅ Done |
| US04 | As a student, I want to receive a push notification when my attendance is successfully marked so that I have confirmation without checking the app. | Medium | 3 hrs | ✅ Done |
| US05 | As an admin, I want to manually override an attendance record so that technical errors (GPS failure, no signal) do not penalise students unfairly. | Low | 4 hrs | ⏳ Carry |
| US06 | As a student, I want my attendance history displayed by subject so that I can track my attendance percentage at any time. | Medium | 5 hrs | ✅ Done |
| US07 | As a teacher, I want to start and end an 'active attendance window' for each class session so that geo-fence marks only trigger during the correct class time. | High | 5 hrs | ✅ Done |

| Sprint 1 Totals | Total Estimated: 35 hrs | Velocity: 7 Stories |
| --- | --- | --- |

# Task 4: GitHub Repository & CI/CD Strategy

## Repository Structure

Repository Name: SDLC-Assignment-[YourName] 📁 /docs/ — Waterfall-Failure-Analysis.pdf, README.md 📁 /backlog/ — Sprint1-Backlog.xlsx, Sprint2-Backlog.xlsx 📁 /src/ — Application source code (future) 📁 /.github/ — CI/CD workflow YAML files 📄 README.md — Full project documentation & CI/CD explanation

## Why CI/CD is Essential for Smart-Attend

Continuous Integration / Continuous Deployment (CI/CD) is the DevOps practice of automatically building, testing, and deploying code changes every time a developer pushes to the repository. For Smart-Attend, which follows a 2-week sprint release cycle, CI/CD is not optional — it is mission-critical.

Continuous Integration (CI) — Every Push, Every Sprint

- Every time a developer pushes code (e.g., the geo-fence engine in Sprint 1), a GitHub Actions workflow automatically triggers a build pipeline.

- The pipeline runs the full automated test suite: unit tests for the geo-fence radius calculator, integration tests for the login API, and UI tests via Detox (React Native testing framework).

- If any test fails, the merge is blocked and the developer is notified immediately — catching bugs in hours, not at the end of the sprint.

Continuous Deployment (CD) — Automatic Sprint Updates to Students

- Once Sprint 1 passes all CI checks and the Sprint Review is approved, the CD pipeline automatically packages the app and pushes it to TestFlight (iOS) and Google Play Internal Testing (Android).

- Students enrolled as beta testers receive an automatic over-the-air (OTA) update notification — no manual distribution needed.

- When Sprint 2 completes (Biometric integration), the same pipeline deploys the update seamlessly. Students get Face ID verification in the next app update without any action from the PM or dev team.

- Environment-specific deployments: 'develop' branch → Staging environment (faculty testing). 'main' branch → Production (live student release).

CI/CD Pipeline Stages for Smart-Attend

| Stage | Tool | Action | Output |
| --- | --- | --- | --- |
| 1 | GitHub Actions | Trigger on every git push to any branch | Pipeline starts |
| 2 | ESLint / Prettier | Code linting and formatting checks | Style pass/fail |
| 3 | Jest | Run 200+ unit tests (geo-fence, auth, notifications) | Test report |
| 4 | Detox | End-to-end UI tests on simulated devices | E2E pass/fail |
| 5 | Fastlane | Build signed .ipa (iOS) and .apk (Android) | Build artifacts |
| 6 | TestFlight / Play | Auto-deploy to beta testers on sprint completion | Student OTA update |

# Conclusion

This assignment demonstrates the critical importance of choosing the right SDLC methodology before committing to a project. The Waterfall Model's sequential, gate-based structure makes it fundamentally incompatible with projects that face evolving requirements — as evidenced by the Dean's mid-development biometric mandate.

By pivoting to the Scrum Framework, the Smart-Attend team can treat the Face ID requirement not as a crisis, but as a normal Product Backlog item to be addressed in Sprint 2. The 2-week sprint cadence ensures early feedback, early testing, and zero 'big bang' release risk.

Finally, implementing a CI/CD pipeline via GitHub Actions and Fastlane transforms the release process from a manual, error-prone ceremony into a fully automated, auditable pipeline — ensuring every sprint update reaches students reliably, consistently, and automatically.

Key Takeaway: Agile + CI/CD = Change-ready projects. Waterfall + late requirements = Project crises. Smart-Attend is built to adapt. Not to fail.