## Sprint 1 — MVP Backlog
🚀 Smart-Attend ¦ Sprint 1 Backlog (MVP) ¦ Weeks 1–2
Goal: Ship MVP — Basic UI, University ID Login, Core Geo-fence Engine ¦ Sprint Duration: 2 Weeks (10 Working Days)
Task ID | User Story (As a..., I want..., So that...) | Category | Priority | Est. Hours | Assigned To | Status | Sprint
US01 | As a student, I want to log in via my university ID and password so that I can securely access my personal attendance profile. | Authentication | High | 4 | Dev – Priya | ✅ Done | Sprint 1
US02 | As a teacher, I want to view a real-time list of students marked present during my class so that I can monitor attendance without a paper register. | Teacher Dashboard | High | 6 | Dev – Rahul | ✅ Done | Sprint 1
US03 | As the system, I want to detect if a student's device GPS is within 10 metres of the classroom coordinates so that attendance is triggered automatically. | Geo-fence Engine | High | 8 | Dev – Arjun | ✅ Done | Sprint 1
US04 | As a student, I want to receive a push notification when my attendance is successfully marked so that I have instant confirmation without opening the app. | Notifications | Medium | 3 | Dev – Priya | ✅ Done | Sprint 1
US05 | As an admin, I want to manually override an attendance record so that genuine technical errors (GPS failure, no signal) do not penalise students. | Admin Controls | Low | 4 | Dev – Rahul | ⏳ Carry-over | Sprint 2
US06 | As a student, I want to see my attendance history organised by subject so that I can track my attendance percentage at any time. | Student Portal | Medium | 5 | Dev – Arjun | ✅ Done | Sprint 1
US07 | As a teacher, I want to open and close an 'active attendance window' for each class session so that geo-fence only marks attendance during the correct class time. | Geo-fence Engine | High | 5 | Dev – Rahul | ✅ Done | Sprint 1
Sprint 1 Totals |  |  |  |  | 7 Stories ¦ Velocity: 31 hrs committed

## Sprint 2 — Biometric Update
🔐 Smart-Attend ¦ Sprint 2 Backlog (Biometric Update) ¦ Weeks 3–4
Goal: Integrate Face ID Verification + Reporting Dashboard Refinement ¦ Sprint Duration: 2 Weeks
Task ID | User Story (As a..., I want..., So that...) | Category | Priority | Est. Hours | Assigned To | Status | Sprint
US05 | As an admin, I want to manually override an attendance record so that technical errors do not penalise students. (Carry-over from Sprint 1) | Admin Controls | Low | 4 | Dev – Rahul | ✅ Done | Sprint 2
US08 | As the system, I want to prompt Face ID / Biometric verification after a geo-fence trigger so that proxy attendance is prevented. | Biometric Module | High | 10 | Dev – Arjun | ✅ Done | Sprint 2
US09 | As a student, I want to use Android Fingerprint/BiometricPrompt as an alternative to Face ID so that the app works on non-Apple devices. | Biometric Module | High | 8 | Dev – Arjun | ✅ Done | Sprint 2
US10 | As a teacher, I want to export my class attendance report as a CSV file so that I can share it with the department coordinator. | Reporting | Medium | 4 | Dev – Priya | ✅ Done | Sprint 2
US11 | As a teacher, I want to view a weekly attendance percentage chart per student so that I can identify at-risk students early. | Reporting | Medium | 5 | Dev – Priya | ✅ Done | Sprint 2
US12 | As the system, I want biometric data to be processed on-device only (no raw data sent to server) so that student privacy is protected. | Privacy & Security | High | 6 | Dev – Rahul | ✅ Done | Sprint 2
US13 | As an admin, I want to run a UAT pilot test with 30 students so that production bugs are caught before the full rollout. | QA / Testing | High | 8 | QA – Divya | ✅ Done | Sprint 2
Sprint 2 Totals |  |  |  |  | 7 Stories ¦ Velocity: 45 hrs committed

## Product Backlog
📋 Smart-Attend ¦ Full Product Backlog
Epic | Story ID | User Story | Priority | Est. Hours | Assigned Sprint | Notes
Auth | US01 | Student login via university ID | High | 4 | Sprint 1
Dashboard | US02 | Teacher real-time attendance list | High | 6 | Sprint 1
Geo-fence | US03 | 10m geo-fence trigger | High | 8 | Sprint 1 | Core feature
Notifications | US04 | Push notification on mark | Medium | 3 | Sprint 1
Admin | US05 | Manual override | Low | 4 | Sprint 2 | Carry-over
Student | US06 | Attendance history by subject | Medium | 5 | Sprint 1
Geo-fence | US07 | Teacher opens/closes window | High | 5 | Sprint 1
Biometric | US08 | Face ID verification (iOS) | High | 10 | Sprint 2 | Dean's requirement
Biometric | US09 | BiometricPrompt (Android) | High | 8 | Sprint 2 | Cross-platform
Reporting | US10 | CSV export | Medium | 4 | Sprint 2
Reporting | US11 | Weekly % chart | Medium | 5 | Sprint 2
Privacy | US12 | On-device biometric processing | High | 6 | Sprint 2 | PDPA compliance
QA | US13 | UAT pilot — 30 students | High | 8 | Sprint 2 | Pre-launch